## Lokesh — UAT Tracker
YLIMS V20.5.2 — UAT Testing Tracker ¦ Lokesh ¦ Server: UAT ¦ 12-05-2026
P1 — Critical ¦ 24 |  |  | P2 — High ¦ 24 |  |  | P3 — Medium ¦ 33 |  | Total : 81
Done: 2 ¦ In Progress: 2 ¦ Pending: 77 ¦ Blocked: 0 ¦ Final Done: 0 ¦ Waiting for Deepak: 2
# | Module | Screen Name | Phase | Basecamp Status | Testing Status | Ready for Product | Remarks | Last Updated
1 | Sample Management | Cancel Sample | P1 | — | Pending
2 |  | Sample Reboking | P1 | — | Pending
3 |  | Archive Samples | P1 | — | Pending
4 |  | TRF Upload | P1 | — | Pending |  | error while gst and pan api hit issue
5 |  | Sample Discard | P2 | — | Pending
6 |  | Sample Discard Report | P2 | — | Pending
7 |  | Upload Weight Slip | P3 | — | Pending
8 |  | Block Sample | P3 | — | Pending
9 |  | Samples Report | P3 | — | Pending
10 |  | Sample Status | P3 | New | Pending |  | Card added — not started by Dev
11 |  | Pending Samples in Lab | P3 | New | Pending |  | Card added — not started by Dev
12 |  | Pending Samples in Department | P3 | New | Pending |  | Card added — not started by Dev
13 |  | Pending Samples for Invoice | P3 | New | Pending |  | Card added — not started by Dev
14 |  | Sample Reports | P3 | New | Pending |  | Card added — not started by Dev
15 | Customer Relation Management | View Client Profile | P1 | Closed by Tester | Done | Waiting for Deepak Approval | Testing complete | 12-05-2026
16 |  | Client Credit Limit | P1 | — | Pending
17 |  | Account Credit | P1 | — | Pending
18 |  | Create New Client | P2 | — | Pending
19 |  | Client Details | P3 | — | Pending
20 |  | Team Target Manage | P3 | — | Pending
21 |  | Create Client Contract | P3 | — | Pending
22 |  | Client Contract | P3 | — | Pending
23 |  | Assign Customer Coordinator/Support | P3 | — | Pending
24 |  | Assign Client Profile | P3 | — | Pending
25 |  | View Followup | P3 | — | Pending
26 |  | Analysis | P3 | — | Pending
27 | Quotation & Pricing | TCS Direct Shipment | P1 | — | Pending
28 | Quality Document Management | Fail Sample | P1 | — | Pending
29 |  | View OOS | P2 | — | Pending
30 |  | New SOP | P2 | — | Pending
31 |  | View SOP | P2 | — | Pending
32 |  | Department SOP | P2 | — | Pending
33 |  | Assign SOP | P2 | — | Pending
34 |  | OOS DashBoard | P2 | — | Pending
35 |  | OOS Answer | P2 | — | Pending
36 |  | OOS Question | P2 | — | Pending
37 | Master Library | Manage Micro RAW Template | P2 | — | Pending
38 | Purchase & Indent | View PO | P2 | — | Pending
39 |  | Generate PO | P2 | In-Progress by Tester | In Progress |  | Testing in progress | 12-05-2026
40 | Reports & COC | Report To Be Compile | P1 | Closed by Tester | Done | Waiting for Deepak Approval | Testing complete | 12-05-2026
41 |  | Report To Be Printed | P1 | Closed by Dev | Pending |  | Dev closed — ready to test | 12-05-2026
42 |  | Reports To Be Dispatching | P1 | Closed by Dev | Pending |  | Dev closed — ready to test | 12-05-2026
43 |  | Report For Signature | P1 | Closed by Dev | Pending |  | Dev closed — ready to test | 12-05-2026
44 |  | Report Review | P1 | — | Pending
45 |  | View Sample for Updation | P1 | — | Pending
46 |  | Allot Sample Report | P1 | — | In Progress
47 |  | Archive Report | P1 | — | Pending
48 |  | Print Coc Report | P1 | — | Pending
49 |  | Print Department Coc Report | P1 | — | Pending
50 |  | COC | P1 | — | Pending
51 |  | COC Department | P1 | — | Pending
52 |  | Modify COC | P1 | — | Pending
53 |  | Extra COC Page | P1 | — | Pending
54 |  | Test Request | P1 | — | Pending
55 |  | Final Report Upload | P2 | — | Pending
56 |  | Upload Amendment Report | P2 | — | Pending
57 |  | Upload Reports | P2 | — | Pending
58 |  | Tracking Report | P2 | — | Pending
59 |  | Booked Courier Report | P2 | — | Pending
60 |  | Approved Test | P2 | — | Pending
61 |  | Assign Power Report | P3 | — | Pending
62 |  | Create Template | P3 | — | Pending
63 |  | Power Report | P3 | — | Pending
64 |  | Dispatch Report | P3 | — | Pending
65 |  | Multi Report | P3 | New | Pending |  | Card added — not started by Dev
66 | Billing and Invoicing | E-Invoice Update | P2 | — | Pending
67 |  | Create Draft Invoice | P2 | — | Pending
68 |  | Update Draft Invoice | P2 | — | Pending
69 |  | Draft Invoice Report | P2 | — | Pending
70 |  | Invoice Assign Dispatch | P3 | — | Pending
71 |  | E-Mail Invoice | P3 | — | Pending
72 |  | Invoice Acknowledgement | P3 | — | Pending
73 |  | Invoice Report | P3 | — | Pending
74 |  | Search Invoice | P3 | — | Pending
75 |  | Invoice Review | P3 | — | Pending
76 | Administration | Audit Trail | P3 | — | Pending
77 |  | Department Creation | P3 | — | Pending
78 |  | Designation Creation | P3 | — | Pending
79 |  | All Department Work Report | P3 | — | Pending
80 | Role Management | Definition of Roles | P3 | — | Pending
81 |  | Create Role | P3 | — | Pending

## Himanshu — UAT Tracker
YLIMS V20.5.2 — UAT Testing Tracker ¦ Himanshu ¦ Server: UAT ¦ 12-05-2026
P1 — Critical ¦ 22 |  | P2 — High ¦ 30 |  | P3 — Medium ¦ 31 |  | Total : 83 |  | Pre-Tested by Lokesh : 24
Done: 24 ¦ In Progress: 4 ¦ Pending: 55 ¦ Blocked: 0 ¦ Final Done: 0 ¦ Waiting for Deepak: 24
# | Module | Screen Name | Phase | Basecamp Status | Tested By | Testing Status | Ready for Product | Remarks | Last Updated
1 | Sample Management | Micro Enter Result | P1 | — | Himanshu | Pending
2 |  | Allot Sample to Department | P1 | — | Himanshu | Pending
3 |  | Received Allot Sample | P1 | — | Himanshu | Pending
4 |  | Dispatch Courier Blue Dart | P1 | — | Himanshu | Pending
5 |  | Rebook Courier | P1 | — | Himanshu | Pending
6 |  | Received Sample | P1 | — | Himanshu | Pending
7 | Reports & COC | Unapproved Test | P1 | Closed by Dev | Himanshu | Pending |  | Dev closed — ready to test | 12-05-2026
8 |  | My Complete Test | P1 | Closed by Dev | Himanshu | Pending |  | Dev closed — ready to test | 12-05-2026
9 |  | Micro Raw Data Enter | P1 | Closed by Dev | Himanshu | Pending
10 |  | Pending Test | P1 | Closed by Dev | Himanshu | Pending
11 |  | Form B | P3 | Closed by Dev | Himanshu | Pending |  | Dev closed — ready to test | 12-05-2026
12 |  | Form B Create | P3 | Closed by Dev | Himanshu | Pending |  | Dev closed — ready to test | 12-05-2026
13 | Billing and Invoicing | Invoice | P1 | — | Himanshu | Pending
14 |  | Invoice Update | P1 | — | Himanshu | Pending
15 |  | E-Invoice Generate | P1 | — | Himanshu | Pending
16 | Purchase & Indent | Client PO | P1 | Closed by Dev | Himanshu | Pending |  | Dev closed — ready to test | 12-05-2026
17 |  | View Client PO | P3 | — | Himanshu | Pending
18 |  | Create Client PO | P3 | — | Himanshu | Pending
19 |  | Indent Manage | P3 | Closed by Dev | Himanshu | Pending
20 |  | Admin Indent Manage | P3 | Closed by Dev | Himanshu | Pending
21 |  | View Indent | P3 | Closed by Dev | Himanshu | Pending
22 | Master Library | Generic Master | P1 | Closed by Tester | Lokesh | Done | Waiting for Deepak Approval | Tested by Lokesh on UAT | 12-05-2026
23 |  | Product Master | P2 | Closed by Tester | Lokesh | Done | Waiting for Deepak Approval | Tested by Lokesh on UAT | 12-05-2026
24 |  | Create Micro Batch | P2 | — | Himanshu | Pending
25 |  | Analyte Master | P2 | — | Himanshu | Pending
26 | Quality Document Management | New STP | P1 | Closed by Tester | Lokesh | Done | Waiting for Deepak Approval | Tested by Lokesh on UAT | 12-05-2026
27 |  | STP Master | P1 | In-Progress by Dev | Himanshu | Pending |  | Dev in progress | 12-05-2026
28 |  | STP Group | P1 | Closed by Tester | Lokesh | Done | Waiting for Deepak Approval | Tested by Lokesh on UAT | 12-05-2026
29 |  | NABL Scope | P1 | Closed by Tester | Lokesh | Done | Waiting for Deepak Approval | Tested by Lokesh on UAT | 12-05-2026
30 |  | Edit STP QA | P2 | In-Progress by Tester | Himanshu | In Progress |  | Testing in progress | 12-05-2026
31 |  | Add STP QA | P2 | In-Progress by Tester | Himanshu | In Progress |  | Testing in progress | 12-05-2026
32 |  | Department STP QA | P2 | In-Progress by Tester | Himanshu | In Progress |  | Testing in progress | 12-05-2026
33 |  | Assign STP QA | P2 | In-Progress by Tester | Himanshu | In Progress |  | Testing in progress | 12-05-2026
34 |  | Map STP Methods | P3 | — | Himanshu | Pending
35 | Quotation & Pricing | Client Product Pricing | P1 | In-Progress by Tester | Himanshu | Pending
36 |  | View Quotation | P1 | In-Progress by Tester | Himanshu | Pending
37 |  | Client Quotation (With Product) | P2 | Closed by Tester | Lokesh | Done | Waiting for Deepak Approval | Tested by Lokesh on UAT | 12-05-2026
38 |  | Client Quotation (Without Product) | P2 | Closed by Tester | Lokesh | Done | Waiting for Deepak Approval | Tested by Lokesh on UAT | 12-05-2026
39 |  | Add Price Book | P2 | Closed by Tester | Lokesh | Done | Waiting for Deepak Approval | Tested by Lokesh on UAT | 12-05-2026
40 |  | View Price Book | P2 | Closed by Tester | Lokesh | Done | Waiting for Deepak Approval | Tested by Lokesh on UAT | 12-05-2026
41 |  | Map Price List to Clients | P2 | — | Himanshu | Pending
42 | Support | Support | P1 | — | Himanshu | Pending
43 |  | Mail Dashboard | P3 | — | Himanshu | Pending
44 |  | Ticket Generate | P3 | — | Himanshu | Pending
45 |  | Ticket Reports | P3 | — | Himanshu | Pending
46 |  | Ticket Reports Admin | P3 | — | Himanshu | Pending
47 | Profile Master | Create Employee | P2 | In-Progress by Tester | Himanshu | Pending |  | Testing in progress
48 |  | Employee Profile | P2 | In-Progress by Tester | Himanshu | Pending |  | Dev closed — ready to test | 12-05-2026
49 |  | Assign Employee Profile | P2 | — | Himanshu | Pending
50 |  | Profile | P2 | In-Progress by Tester | Himanshu | Pending
51 | Document Management System | Method Upload | P2 | Closed by Tester | Lokesh | Done | Waiting for Deepak Approval | Tested by Lokesh on UAT | 12-05-2026
52 |  | Method Validation Upload | P2 | Closed by Tester | Lokesh | Done | Waiting for Deepak Approval | Tested by Lokesh on UAT | 12-05-2026
53 |  | Method Development | P2 | — | Himanshu | Pending
54 |  | View Method Development | P2 | — | Himanshu | Pending
55 |  | View Validation Method | P2 | Closed by Tester | Lokesh | Done | Waiting for Deepak Approval | Tested by Lokesh on UAT | 12-05-2026
56 |  | View Method | P3 | Closed by Tester | Lokesh | Done | Waiting for Deepak Approval | Tested by Lokesh on UAT | 12-05-2026
57 | Equipment Management | View Equipment | P2 | Closed by Tester | Lokesh | Done | Waiting for Deepak Approval | Tested by Lokesh on UAT | 12-05-2026
58 |  | Equipment PM | P2 | Closed by Tester | Lokesh | Done | Waiting for Deepak Approval | Tested by Lokesh on UAT | 12-05-2026
59 |  | Equipment EquipmentOnOff | P2 | — | Himanshu | Pending
60 |  | Equipment Assign to Employee | P3 | Closed by Tester | Lokesh | Done | Waiting for Deepak Approval | Tested by Lokesh on UAT | 12-05-2026
61 |  | View Equipment Issue | P3 | — | Himanshu | Pending
62 |  | Equipment Registration | P3 | Closed by Tester | Lokesh | Done | Waiting for Deepak Approval | Tested by Lokesh on UAT | 12-05-2026
63 |  | View Equipment Status | P3 | Closed by Tester | Lokesh | Done | Waiting for Deepak Approval | Tested by Lokesh on UAT | 12-05-2026
64 |  | Equipment Transfer | P3 | Closed by Tester | Lokesh | Done | Waiting for Deepak Approval | Tested by Lokesh on UAT | 12-05-2026
65 |  | View Equipment Transfer | P3 | Closed by Tester | Lokesh | Done | Waiting for Deepak Approval | Tested by Lokesh on UAT | 12-05-2026
66 |  | Equipment PM Approve | P3 | Closed by Tester | Lokesh | Done | Waiting for Deepak Approval | Tested by Lokesh on UAT | 12-05-2026
67 |  | Equipment Dashboard | P3 | — | Himanshu | Pending
68 | Inventory Management | New CRM | P2 | — | Himanshu | Pending
69 |  | CRM Working Standard | P2 | Closed by Tester | Lokesh | Done | Waiting for Deepak Approval | Tested by Lokesh on UAT | 12-05-2026
70 |  | User Tracking Report | P2 | — | Himanshu | Pending
71 |  | Add Column | P2 | Closed by Tester | Lokesh | Done | Waiting for Deepak Approval | Tested by Lokesh on UAT | 12-05-2026
72 |  | View Column | P2 | Closed by Tester | Lokesh | Done | Waiting for Deepak Approval | Tested by Lokesh on UAT | 12-05-2026
73 |  | View CRM | P2 | — | Himanshu | Pending
74 | Administration | Add IP Address | P3 | — | Himanshu | Pending
75 | Customer Relation Management | Create Opportunity | P3 | — | Himanshu | Pending
76 |  | View Opportunity | P3 | — | Himanshu | Pending
77 |  | Lead | P3 | — | Himanshu | Pending
78 |  | Web Lead | P3 | — | Himanshu | Pending
79 |  | View Lead | P3 | — | Himanshu | Pending
80 |  | Opportunity | P3 | — | Himanshu | Pending
81 |  | Lead Contact | P3 | — | Himanshu | Pending
82 |  | Lead Opportunity | P3 | — | Himanshu | Pending
83 |  | Lead for Quotation | P3 | — | Himanshu | Pending